## Sheet2
Hwange Rural District Council Annual Procurement Plan for FY ____2025__
Ref No. | Class of Procurement | Object Code | Description of Requirements | PMU/End-User | Procurement Method | Prequalification/EOI (Y/N) |  | Schedule for Each Procurement Activity | [6 empty] | Source of Funds | Estimated Budget (USD) | [5 empty] | Comments
[6 empty] | EOI Publication Date | EOI Closing Date | Bid Notice Publication Date | Bid Closing Date | Publication of Award Notice | Contract Signing | Cycle(work days) Bid notice - Award notice | Lead Time (delivered time) Contract signing to expect. delivery | SPOC (Y/N) |  | Unit of Measurement (UoM) | Quantity | Unit Price | Total(MOOE+CO) | MOOE | CO
HRDC 01/2025 | Goods | 25100000 | Motor vihecles for management | Management | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-06-06 | 2025-07-22 | 2025-09-05 | 2025-10-20 | 90 | 2025-11-26 | Y | Internally Generated Funds | Number | 10 | 56000 | 560000 | 0 | 495000 | It is a domestic Tender.Tender to be advertised as and when funds are available
HRDC 01/2025 | Goods | 25100000 | Pool motor vihecles | Council Staff | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-06-06 | 2025-07-22 | 2025-09-05 | 2025-10-20 | 90 | 2025-11-26 | Y | Internally Generated Funds | Number | 5 | 30000 | 150000 | - | 150000 | It is a domestic Tender.Tender to be advertised as and when funds are available
HRDC 02/2025 | Goods | 22100000 | Excavator(22000 tonne) | Engineering | Competitive Bidding Method | Not Applicable | Not Applicable | 2024-03-07 | 2025-04-04 | 2025-05-07 | 2025-06-03 | 59 | 2025-06-30 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 80000 | 80000 | 0 | 80000 | It is a domestic Tender.Procurement uses Devolution funds
HRCD03/2025 | Goods | 25100000 | Ambulance | Social services | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-02-28 | 2025-04-02 | 2025-05-02 | 2025-05-29 | 82 | 2025-06-30 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 60000 | 60000 | 0 | 60000 | It is a domestic Tender.Procurement uses Devolution funds
HRDC01/2025 | Goods | 25100000 | Mini bus 32 seater | Human resources and Administration | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-06-06 | 2025-07-22 | 2025-09-05 | 2025-10-20 | 88 | 2025-11-28 | N | Internally Generated Funds | Number | 1 | 45000 | 45000 | 0 | 40000 | It is a domestic Tender.Tender to be advertised as and when funds are available
HRDC 04/2025 | Goods | 25173107 | Dumpy level Equipment | Engineering | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-17 | 2025-03-21 | 2025-03-24 | 2025-03-24 | 8 | 2025-03-31 | N | Internally Generated Funds | Number | 1 | 500 | 500 | 0 | 500 | Procurement to be done when funds are available
HRDC05/2025 | Goods | 25160000 | Motorbikes | Coucillors and Administration | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-08-08 | 2025-09-08 | 2025-10-06 | 2025-10-30 | 77 | 2025-11-27 | N | Internally Generated Funds | Number | 29 | 1500 | 43500 | 0 | 43500 | It is a domestic Tender.Tender to be advertised as and when funds are available
HRDC06/2025 | Non -Complex Works | 72000000 | Installation of resevour tanks at Council main office | Engineering | Request For Quotation method | Not Applicable | Not Applicable | 2025-04-14 | 2025-04-22 | 2025-04-23 | 2025-04-23 | 10 | 2025-04-30 | N | Internally Generated Funds | Number | 1 | 2000 | 2000 | 0 | 2000 | Procurement to be done when funds are available
HRDC07/2025 | Non-Complex works | 39111608 | Installation of street lights at Dete | Engineering | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-13 | 2025-03-19 | 2025-03-20 | 2025-03-20 | 7 | 2025-03-27 | N | Internally Generated Funds | Number | 20 | 500 | 10000 | 0 | 10000 | Procurement to be done when funds are available.The works are non complex
HRDC07/2025 | Non-Complex works | 39111608 | Installation of solar lights at Cross Dete and Dete Shopping areas including Dete Sub Office | Engineering | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-13 | 2025-03-19 | 2025-03-20 | 2025-03-20 | 7 | 2025-03-27 | N | Internally Generated Funds | Number | 40 | 150 | 6000 | - | 6000 | Procurement to be done when funds are available.The works are non complex
HRDC08/2024 | Non-Complex works | 72000000 | Construction of a conference center | Engineering | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-30 | 2025-06-23 | 2025-07-21 | 2025-08-18 | 75 | 2025-12-31 | N | Internally Generated Funds | Number | 1 | 68942.55 | 68942.55 | 0 | 68942.55 | It is a Domestic Tender.Procurement to be done when funds are available.works(Non Complex)
HRDC09/2025 | Non-Complex works | 72000000 | Construction of Staff houses | Engineering | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-10 | 2025-01-30 | 2025-02-27 | 2025-03-25 | 52 | 2025-07-31 | N | Internally Generated Funds | Number | 2 | 35000 | 70000 | 0 | 70000 | It is a Domestic Tender.Procurement to be done when funds are available.works(Non Complex)
HRDC10/2025 | Non-Complex works | 72000000 | Construction of toilets at Dete Sub office | Engineering | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-25 | 2025-05-27 | 2025-06-23 | 2025-07-16 | 59 | 2025-08-28 | N | Internally Generated Funds | Number | 1 | 6000 | 6000 | - | 6000 | It is a Domestic Tender.Procurement to be done when funds are available.works(Non Complex)
HRDC11/2025 | Non-Complex works | 72000000 | Reconstruction of Council offices | Engineering | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-31 | 2025-02-27 | 2025-03-26 | 2024-04-22 | 54 | 2025-08-29 | N | Internally Generated Funds | Number | 1 | 120000 | 120000 | - | 120000 | It is a Domestic Tender.Procurement to be done when funds are available.works(Non Complex)
HRDC12/2025 | Consultancy services | 80101504 | Architectural Services | Engineering/Planning | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-06-20 | 2025-07-24 | 2025-08-22 | 2025-09-19 | 64 | 2025-10-31 | N | Internally Generated Funds | Number | 1 | 10000 | 10000 | 10000 | 0 | It is a Domestic Tender.Procurement to be done when funds are available
HRDC13/2025 | Consultancy services | 80101504 | Development of a local master plan(Monde and Batoka) | Engineering | Expression of Interest | 2025-03-10 | 2025-04-11 | 2025-05-21 | 2025-06-09 | 2025-07-14 | 2025-08-04 | 97 | 2025-10-03 | Y | Special Account - Locally Funded/Domestic Grants Fund | Number | 2 | 70000 | 140000 | 140000 | 0 | Procurement uses Devolution disbursments.It is a domestic tender
HRDC14/2025 | Goods | 49121503 | Ranger cabins | Environment | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-13 | 2025-02-07 | 2025-03-10 | 2025-04-01 | 56 | 2025-04-30 | N | Internally Generated Funds | Number | 8 | 1500 | 12000 | 0 | 12000 | It is a domestic Tender. Procurement to be done when funds are available
HRDC15/2025 | Goods | 43190000 | Communication radios | Security | Request For Quotation method | Not Applicable | Not Applicable | 2025-02-13 | 2025-02-20 | 2025-02-24 | 2025-02-24 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 7 | 100 | 700 | 0 | 700 | Procurement to be done when funds are available
HRDC16/2025 | Goods | 42140000 | Medical supplies | Clinics | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-11 | 2025-05-13 | 2025-06-10 | 2025-07-04 | 57 | 2025-07-31 | N | Internally Generated Funds | Number | 10000 | 0.83 | 12000 | 12000 | 0 | It is a domestic Tender. Procurement to be done when funds are available
HRDC17/2025 | Non-Complex works | 72000000 | Construction of a Weighing bridge | Environment | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-30 | 2025-02-27 | 2025-03-26 | 2025-04-22 | 56 | 2025-08-29 | N | Internally Generated Funds | Number | 1 | 150000 | 150000 | 0 | 150000 | It is a Domestic Tender.Tender to be done when funds are available
HRDC18/2025 | Non-Complex works | 72000000 | Construction of cottage at Songwa clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-03-06 | 2025-04-03 | 2025-05-06 | 2025-05-30 | 57 | 2025-09-30 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 2 | 35000 | 70000 | 0 | 70000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC19/2024 | Non-Complex works | 72000000 | Construction of cottages at Dinde primary | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-02 | 2025-05-30 | 2025-06-27 | 2025-07-23 | 77 | 2025-11-28 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 2 | 75000 | 75000 | 0 | 75000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC20/2025 | Non-Complex works | 72000000 | Construction of Mashala clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-03-14 | 2025-05-05 | 2025-06-20 | 2025-07-23 | 90 | 2025-11-28 | Y | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 300000 | 30000 | 0 | 30000 | It is Domestic Tender.Procurement uses Devolution disbursments
HRDC21/2025 | Non-Complex works | 72000000 | Construction of Cottage at Nembila Secondary school | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-25 | 2025-05-28 | 2025-06-25 | 2025-07-21 | 60 | 2025-11-28 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 2 | 35000 | 70000 | 0 | 70000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC22/2025 | Non-Complex works | 72000000 | Construction of cottage and classroom block at Chikamba Primary school | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2024-03-07 | 2025-05-06 | 2025-06-18 | 2025-07-18 | 91 | 2025-11-29 | Y | Special Account - Locally Funded/Domestic Grants Fund | Number | 2 | 45000 | 90000 | 0 | 90000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC23/2025 | Non-Complex works | 72000000 | Construction of main clinic block at Chikandakubi | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-24 | 2025-02-20 | 2025-03-21 | 2025-04-23 | 61 | 2025-08-31 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 100000 | 100000 | 0 | 100000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC24/2025 | Non-Complex works | 72000000 | Completion of a flee market at Cross Dete | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-03-28 | 2025-04-29 | 2025-05-29 | 2025-06-24 | 59 | 2025-07-31 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 25000 | 25000 | 0 | 25000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC25/2025 | Non-Complex works | 72000000 | Completion of classroom block at Songwa Secondary | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-02-14 | 2025-03-14 | 2025-04-11 | 2025-05-12 | 65 | 2025-06-30 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 45000 | 45000 | 0 | 45000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC26/2025 | Non-Complex works | 72000000 | Installation of a 5000l jojotank at Dete Sub Office&clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-17 | 2025-02-17 | 2025-03-18 | 2025-04-11 | 60 | 2025-05-30 | N | Internally Generated Funds | Number | 3 | 2500 | 7500 | 0 | 7500 | It is a Domestic Tender.Procurement is doner funded
HRDC27/2025 | Non-Complex works | 72000000 | Construction of classroom block at Vulindlela secondary | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-03 | 2025-01-31 | 2025-03-03 | 2025-03-27 | 55 | 2025-07-31 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 45000 | 45000 | 0 | 45000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC28/2025 | Non-Complex works | 72000000 | Construction of staff cottages at Simangani clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-04 | 2025-05-06 | 2025-06-04 | 2025-06-30 | 58 | 2025-10-31 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 35000 | 35000 | 0 | 35000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC29/2025 | Non-Complex works | 72000000 | Construction of main clinic block at Breakfast ,Matesti | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-03-28 | 2025-05-09 | 2025-06-09 | 2025-07-03 | 66 | 2025-09-30 | N | Donor funding | Number | 1 | 100000 | 100000 | 0 | 100000 | It is a Domestic Tender.Procurement is Donor funded
HRDC30/2025 | Non-Complex works | 72000000 | Completion of Batoka clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-10 | 2025-02-10 | 2025-03-11 | 2025-04-04 | 59 | 2025-06-30 | N | Donor funding | Number | 1 | 110000 | 110000 | 0 | 110000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC31/2025 | Goods | 32000000 | Airconditioners for clinic pharmacies and Council boardroom | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-11-07 | 2025-11-19 | 2025-11-20 | 2025-11-20 | 8 | 2025-11-28 | N | Internally Generated Funds | Number | 6 | 700 | 4200 | 0 | 4200 | Procurement to be done when funds are available
HRDC32/2025 | Non-Complex works | 72000000 | Construction of classroom Block Chenambi Secondary | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-04 | 2025-05-07 | 2025-06-05 | 2025-06-30 | 58 | 2025-10-31 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 1 | 45000 | 45000 | 0 | 45000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC33/2025 | Non-Complex works | 72000000 | Construction of Health Post Lumbora, Sidinda | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-03-14 | 2025-04-08 | 2025-05-07 | 2025-06-02 | 53 | 2025-09-30 | N | Donor funding | Number | 1 | 80000 | 80000 | 0 | 80000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC34/2025 | Non-Complex works | 72000000 | Construction of Health Post Sikabelo Matesti | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-02-28 | 2025-03-27 | 2025-04-28 | 2025-05-27 | 59 | 2025-08-29 | N | Donor funding | Number | 1 | 80000 | 80000 | 0 | 80000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC35/2025 | Goods | 42190000 | Equipmet and furniture for Mashala Clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-08-15 | 2025-09-10 | 2025-10-08 | 2025-11-03 | 57 | 2025-11-28 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 45 | 1333.33 | 60000 | 0 | 60000 | It is a Domestic Tender.Procurement uses Devolution disbursments
HRDC36/2025 | Goods | 42190000 | Equipmet and furniture for Breakfast Clinic | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-04 | 2025-05-07 | 2025-06-05 | 2025-07-03 | 61 | 2025-07-31 | N | Donor funding | Number | 45 | 1333 | 60000 | 0 | 60000 | It is a Domestic Tender.Procurement is Donor funded
HRDC37/2025 | Non-Complex works | 72141120 | Sewer reticulation-Kamativi Sub Office | HWange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-06-16 | 2025-07-14 | 2025-08-13 | 2025-09-08 | 59 | 2025-11-28 | N | Donor funding | Number | 1 | 300000 | 300000 | 0 | 300000 | It is a Domestic Tender. Tender to be advertised as and when funds are available
HRDC38/2025 | Non-Complex works | 72000000 | Rehabilitation of water treatment plant at Kamativi | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-10-10 | 2025-10-17 | 2025-10-23 | 2025-10-23 | 10 | 2025-10-31 | N | Donor funding | Kms | 1 | 26904.7 | 26904.7 | 0 | 26904.7 | Procurement to be processed when finds arises.It is a domestic tender
HRDC39/2025 | Non-Complex works | 72141120 | Sewer reticulation-Dete | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-25 | 2025-06-17 | 2025-07-29 | 2025-09-01 | 92 | 2025-11-28 | Y | Special Account - Locally Funded/Domestic Grants Fund | Kms | 1 | 920000 | 920000 | 0 | 920000 | It is a Domestic Tender. Tender to be advertised as and when funds are available
HRDC40/2025 | Non-Complex works | 71120000 | Borehole drilling and solarisation | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-06-16 | 2025-07-14 | 2025-08-13 | 2025-09-08 | 59 | 2025-09-30 | N | Donor funding | Number | 42 | 4500 | 189000 | 0 | 189000 | It is a Domestic Tender.Procurement is donor funded
HRDC41/2025 | Non-Complex works | 71120000 | Rehabilitation of boreholes | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-07-18 | 2025-08-20 | 2025-09-17 | 2025-10-13 | 60 | 2025-10-31 | N | Donor funding | Number | 40 | 6000 | 240000 | 0 | 240000 | It is a Domestic Tender.Procurement is donor funded
HRDC42/2025 | Goods | 43231503 | Procurement and installation of Housing Software | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-04-25 | 2025-05-27 | 2025-06-24 | 2025-07-14 | 55 | 2025-08-31 | N | Internally Generated Funds | Number | 1 | 60000 | 60000 | 0 | 60000 | It is a Domestic Tender. Tender to be advertised as and when funds are available
HRCD43/2025 | Goods | 43231503 | National flags with ropes | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-14 | 2025-03-21 | 2025-03-24 | 2025-03-24 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 13 | 18 | 216 | 0 | 216 | Procurement to be done when need arises.
HRDC44/2025 | Goods | 43000000 | Printers | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 2 | 1250 | 2500 | 0 | 2500 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | Desktops | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 4 | 800 | 3200 | 0 | 3200 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | Cellphones | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 15 | 500 | 7500 | 0 | 7500 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | Shredding machine | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 1 | 100 | 100 | 0 | 100 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | Laptops | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 17 | 1564.71 | 26600 | 0 | 26600 | It is a Domestic Tender. Procurement to be done when needs arises, Procurement of two laptops were exempted ref PRAZ/D/R/2022
HRDC44/2025 | Goods | 43000000 | Television | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 2 | 700 | 1400 | 0 | 1400 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | Binding machine | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 10 | 30 | 300 | 0 | 300 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | Decoder | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 2 | 600 | 1200 | 0 | 1200 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | PA System | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 1 | 1500 | 1500 | 0 | 1500 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC44/2025 | Goods | 43000000 | ICT Tools box) | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-19 | 2025-07-17 | 2025-08-14 | 62 | 2025-08-31 | N | Internally Generated Funds | Number | 1 | 300 | 300 | 0 | 300 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC45/2025 | Goods | 43000000 | Cartridges | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-02-07 | 2025-02-17 | 2025-02-24 | 2025-02-24 | 9 | 2025-02-28 | N | Internally Generated Funds | Number | 69 | 70 | 4830 | 4830 | 0 | It is a Domestic Tender. Procurement to be done when needs arises
HRDC46/2025 | Consultancy services | 43000000 | Upgrading of Accounting software and Installation in Sub Offices | Hwange Rural District Council | Direct Procurement Method | Not Applicable | Not Applicable | 2025-01-31 | 2025-03-03 | 2025-03-31 | 2025-04-30 | 61 | 2025-05-31 | N | Internally Generated Funds | Number | 1 | 35116.33 | 35116.33 | 35116.33 | 0 | It is a domestic Tender. Procurement to be done when need arises
HRDC47/2025 | Goods | 43000000 | Installation of Internet at Sub offices | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-04-07 | 2025-04-16 | 2025-04-17 | 2025-04-17 | 9 | 2025-04-30 | N | Internally Generated Funds | Number | 1 | 8000 | 8000 | 0 | 8000 | Council will adopt Expression of Interest. Procurement will be done when funds are available
HRDC48/2025 | Goods | 56000000 | Desks | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2015-04-11 | 2025-05-20 | 2025-06-18 | 2025-07-14 | 63 | 2025-07-31 | N | Internally Generated Funds | Number | 15 | 453.33 | 6800 | 0 | 6800 | It is a domestic tender.Procurement to be done when need arises
HRDC48/2025 | Goods | 56000000 | Chairs | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2015-04-11 | 2025-05-20 | 2025-06-18 | 2025-07-14 | 63 | 2025-07-31 | N | Internally Generated Funds | Number | 23 | 652.61 | 15010 | 0 | 15010 | It is a domestic tender.Procurement to be done when need arises
HRDC48/2025 | Goods | 56000000 | Boardroom furniture | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2015-04-11 | 2025-05-20 | 2025-06-18 | 2025-07-14 | 63 | 2025-07-31 | N | Internally Generated Funds | Number | 1 | 14000 | 14000 | 0 | 14000 | It is a domestic tender.Procurement to be done when need arises
HRDC48/2025 | Goods | 56000000 | Steel cabinets | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2015-04-11 | 2025-05-20 | 2025-06-18 | 2025-07-14 | 63 | 2025-07-31 | N | Internally Generated Funds | Number | 9 | 553.33 | 4980 | 0 | 4980 | It is a domestic tender.Procurement to be done when need arises
HRDC49/2025 | Goods | 47000000 | Cleaning detergants | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-01-13 | 2025-01-22 | 2025-01-23 | 2025-01-23 | 7 | 2025-01-31 | N | Internally Generated Funds | Number | 587 | 15.32 | 8805 | 8805 | 0 | Procurement will be done as and when need arises
HRDC50/2025 | Goods | 47000000 | cleaning equipment | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-03 | 2025-03-10 | 2025-03-13 | 2025-03-17 | 11 | 2025-03-31 | N | Internally Generated Funds | Number | 319 | 5.55 | 1914 | - | 1914 | Procurement will be done as and when need arises
HRDC51/2025 | Goods | 46100000 | Fire Arms | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-09 | 2025-06-12 | 2025-07-10 | 2025-08-07 | 64 | 2024-08-29 | N | Internally Generated Funds | Number | 4 | 4000 | 16000 | 0 | 16000 | It is a domestic Tender. Procurement to be done when need arises
HRDC52/2025 | Goods | 25173107 | GPS Machines and drone | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-05-16 | 2025-06-13 | 2025-07-11 | 2025-08-01 | 65 | 2025-08-29 | N | Internally Generated Funds | Number | 7 | 1821.43 | 12750 | 0 | 12750 | It is a Domestic Tender.Procurement to be done when funds are available
HRDC53/2025 | Goods | 41111509 | Digital weighing scale | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-14 | 2025-03-20 | 2025-03-24 | 2025-03-24 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 1 | 1000 | 1000 | 0 | 1000 | Procurement to be done when need arises
HRDC54/2025 | Non consultancy | 82100000 | Advertising | Hwange Rural District Council | Direct Procurement Method | Not Applicable | Not Applicable | 2025-04-22 | 2025-04-23 | 2025-04-24 | 2025-04-28 | 5 | 2025-04-30 | N | Internally Generated Funds | Number | 43 | 665.35 | 28610 | 28610 | 0 | Procurement to be done when need arises
HRDC55/2025 | Non-Complex works | 52131500 | Boardroom and Office curtaining | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-09-11 | 2025-09-19 | 2025-09-22 | 2025-09-22 | 8 | 2025-09-29 | N | Internally Generated Funds | Number | 9 | 600 | 5400 | 0 | 5400 | Procurement to be done when need arises
HRDC56/2025 | Consultancy services | 80101504 | Revaluation of Assets | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-07-28 | 2025-08-27 | 2025-09-24 | 2025-10-20 | 59 | 2025-11-28 | N | Internally Generated Funds | Number | 1 | 25000 | 25000 | 25000 | 0 | It is a domestic Tender. Procurement to be done when funds are available
HRDC57/2025 | Goods | 15100000 | Fuels and lubricants for ERRP Projects | Hwange Rural District Council | Direct Procurement Method | Not Applicable | Not Applicable | 2025-02-17 | 2025-02-19 | 2025-02-20 | 2025-02-24 | 5 | 2025-02-28 | Y | Special Account - Locally Funded/Domestic Grants Fund | Litres | 54000 | 2 | 108000 | 108000 | 0 | It is a Domestic Tender.Procurement is funded by Zinara disbursement.Council will do ramwork Agreements
HRDC58/2025 | Goods | 55121706 | Roll up banners | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-14 | 2025-03-21 | 2025-03-24 | 2025-03-24 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 10 | 80 | 800 | 800 | 0 | Procurement will be done as and when funds are available
HRDC59/2025 | Goods | 14110000 | Stationery | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-01-13 | 2024-01-23 | 2025-01-24 | 2025-01-24 | 10 | 2025-01-31 | N | Internally Generated Funds | Number | 2007 | 3.39 | 8500 | 8500 | 0 | Procurement will be done as and when need arises
HRDC60/2025 | Non consultancy | 82121500 | Printing | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-04-07 | 2025-04-16 | 2025-04-17 | 2025-04-17 | 9 | 2025-04-30 | N | Internally Generated Funds | Pages | 1 | 1000 | 1000 | 1000 | 0 | Procurement to be done when need arises
HRDC61/2025 | Goods | 46100000 | Ammunition and accessories | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2024-03-10 | 2025-03-18 | 2025-03-19 | 2025-03-19 | 8 | 2025-03-31 | N | Internally Generated Funds | Number | 400 | 22 | 8800 | 0 | 8800 | Procurement to be done when need arises
HRDC62/2025 | Goods | 27110000 | Small tools(hardware | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-08-08 | 2025-08-20 | 2025-08-21 | 2025-08-21 | 8 | 2025-08-29 | N | Internally Generated Funds | Number | 133 | 61.43 | 817.75 | 8170.75 | 0 | Procurement to be done when need arises
HRDC63/2025 | Non-Complex works | 72141106 | Road maintenance | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2024-03-14 | 2025-05-12 | 2025-06-25 | 2025-07-25 | 93 | 2025-11-28 | Y | Special Account - Locally Funded/Domestic Grants Fund | Kms | 140 | 2579.2 | 361088.08 | 361088.08 | 0 | It is a Domestic Tender. Procurement funded by Zinara disbursement
HRDC64/2025 | Goods | 56101526 | Office Refrigarators and dispensor | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-07-10 | 2025-07-18 | 2025-07-22 | 2025-07-22 | 9 | 2025-07-31 | N | Internally Generated Funds | Number | 11 | 350 | 3850 | 0 | 3850 | Procurement to be done when need arises and there is availability of funds
HRDC65/2025 | Goods | 46180000 | Protective Clothing | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-07-30 | 2025-08-15 | 2025-08-18 | 2025-08-18 | 15 | 2025-08-29 | N | Internally Generated Funds | Number | 304 | 17.3 | 5168.5 | 5168.5 | 0 | Procurement to be done when need arises
HRDC66/2025 | Goods | 53100000 | Corporate wear | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-09-01 | 2025-09-12 | 2025-09-15 | 2025-09-15 | 11 | 2025-09-30 | N | Internally Generated Funds | Number | 587 | 10.69 | 6457 | 6457 | 0 | Procurement to be done when need arises
HRDC67/2025 | Goods | 90141503 | Exhibition material(Agricultural shows&ZITF) | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-03 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 11 | 2025-03-31 | N | Internally Generated Funds | Number | 20 | 250 | 5000 | 5000 | 0 | Procurement to be done when need arises
HRDC68/2025 | Goods | 48102110 | Christmas hampers | Councillors&employees | Request For Quotation method | Not Applicable | Not Applicable | 2025-10-27 | 2025-11-03 | 2025-11-10 | 2025-11-10 | 12 | 2025-11-28 | N | Internally Generated Funds | Number | 38 | 50 | 1900 | 1900 | 0 | Procurement to be done when need arises
HRDC69/2025 | Goods | 83101510 | Office provisions(mineral water) | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-01-21 | 2025-01-24 | 2025-01-27 | 2025-01-27 | 5 | 2025-01-31 | N | Internally Generated Funds | Number | 625 | 6 | 3750 | 3750 | 0 | Procurement to be done when need arises
HRDC70/2025 | Non consultancy | 78181500 | Repairs and maintenance of motor vihecles&motorbikes | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2024-05-23 | 2025-06-25 | 2025-07-22 | 2025-08-18 | 59 | 2025-08-29 | N | Internally Generated Funds | Number | 13 | 10653.84 | 138500 | 138500 | 0 | It is a domestic Tender. Procurement to be done when need arises
HRDC71/2025 | Non consultancy | 78181500 | Servicing of motor vihecles | Hwange Rural District Council | Direct Procurement Method | Not Applicable | Not Applicable | 2025-06-27 | 2025-07-21 | 2025-08-20 | 2025-09-15 | 55 | 2025-09-30 | N | Internally Generated Funds | Number | 13 | 5815.3 | 75599 | 75599 | 0 | Procurement to be done when need arises
HRDC72/2025 | Non consultancy | 72100000 | Repair and maintanence of Council buildings | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-07-25 | 2025-08-25 | 2025-09-22 | 2025-11-03 | 27 | 2025-11-28 | N | Internally Generated Funds | Number | 13 | 10929.23 | 142080 | 142080 | 0 | Its domestic tender.Procurement will be done when need arises.
HRDC73/2025 | Non complex works | 60104701 | maintanance of solar systems at Council offices | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-07 | 2025-04-07 | 2025-05-08 | 2025-06-04 | 60 | 2025-08-29 | N | Internally Generated Funds | Number | 3 | 1000 | 3000 | 3000 | 0 | It is a domestic Tender. Procurement will be done when funds are available
HRDC74/2025 | Non consultancy | 46101500 | Fire arms maintenance | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-17 | 2025-03-21 | 2025-03-24 | 2025-03-24 | 6 | 2025-03-31 | N | Internally Generated Funds | Number | 5 | 350 | 1750 | 1750 | 0 | Procurement to be done when need arises
HRDC75/2025 | None consultancy | 56000000 | Furniture repairs | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-10 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 6 | 2025-03-31 | N | Internally Generated Funds | Number | 20 | 150 | 3000 | 3000 | 0 | Procurement to be done when need arises
HRDC76/2025 | Consultancy services | 43231601 | Renewal of Accounting softwares(Quantrax&Pastel | hwange Rural District Council | Direct Procurement Method | Not Applicable | Not Applicable | 2025-03-10 | 2025-03-12 | 2025-03-13 | 2025-03-17 | 6 | 2025-03-31 | N | Internally Generated Funds | Number | 2 | 9000 | 18000 | 18000 | 0 | Procurement to be done when need arises
HRDC77/2025 | Consultancy services | 43231601 | Maintance Of Accounting software &PBX | Hwange Rural District Council | Direct Procurement Method | Not Applicable | Not Applicable | 2025-04-07 | 2025-04-09 | 2025-04-10 | 2025-04-16 | 8 | 2025-04-30 | N | Internally Generated Funds | Number | 1 | 12400 | 12400 | 12400 | 0 | Procurement to be done when need arises
HRDC78/2025 | Goods | 43233205 | Procurement of an Antivirus | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-04-07 | 2025-04-16 | 2025-04-16 | 2025-04-16 | 8 | 2025-04-30 | N | Internally Generated Funds | Number | 1 | 7500 | 7500 | 7500 | - | Procurement to be done when need arises
HRDC79/2025 | Non consultancy | 43211600 | Laptops Repairs | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-07 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 2 | 100 | 200 | 200 | 0 | Procurement to be done when need arises
HRDC79/2025 | Non consultancy | 43211600 | Repairs of desktops | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-07 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 2 | 500 | 1000 | 1000 | 0 | Procurement to be done when need arises
HRDC79/2025 | Non consultancy | 43211600 | repairs of printers | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-07 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 2 | 500 | 100 | 1000 | 0 | Procurement to be done when need arises
HRDC79/2025 | Non consultancy | 43211600 | repairs of external drive | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-07 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 2 | 150 | 300 | 300 | 0 | Procurement to be done when need arises
HRDC80/2025 | Non consultancy | 72151207 | Repairs,service and maintanance of air conditioners | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-17 | 2025-03-24 | 2025-03-25 | 2025-03-25 | 7 | 2025-03-31 | N | Internally Generated Funds | Number | 15 | 150 | 2250 | 2250 | 0 | Procurement to be done when need arises
HRDC81/2025 | Non consultancy | 25101801 | Maintainance of motorbikes | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-03-10 | 2025-03-14 | 2025-03-17 | 2025-03-17 | 6 | 2025-03-31 | N | Internally Generated Funds | Number | 36 | 133 | 4800 | 4800 | - | Procurement to be done when need arises
HRDC82/2025 | Goods | 25172500 | Tyres (light and heavy duty vehicles) | Hwange Rural District Council | Competitive Bidding Method | Not Applicable | Not Applicable | 2025-01-24 | 2025-02-24 | 2025-03-24 | 2025-04-17 | 59 | 2025-04-30 | N | Internally Generated Funds | Number | 52 | 338 | 17600 | 17600 | - | It is a domestic tender. Procurement to be done when need arises
HRDC83/2025 | Goods | 30130000 | building materials | Hwange Rural District Council | Request For Quotation method | Not Applicable | Not Applicable | 2025-06-02 | 2025-06-12 | 2025-06-16 | 2025-06-16 | 11 | 2025-06-30 | N | Special Account - Locally Funded/Domestic Grants Fund | Number | 120 | 79 | 9500 | 9500 | - | Procurement is campfire funded. Procurement to be done when need arises
Prepared by : Nomagugu D Makhetho(Procurement Officer)
Approved by: Phindile Ncube(Chief Executive Officer

## Column Description
A. The APP should include all procurement activities planned for the year. The approved APP shall be the basis for the Procuring Entity’s procurement, and only those projects / procurement included therein shall be undertaken. B. The APP shall include only those procurements that are considered crucial to the efficient discharge of governmental functions. C. Before uploading in the system, kindly take approval from of the accounting officer or HOD.
Abbreviation/Coulmn Heads | Description
Ref. No | PE's own itemwise referene number
Class of Procurement | Goods/Works(Complex)/Works(Non Complex)/Non Consultancy/Consultancy
Object Code | Item Category Code(UNSPSC)- Pick the relevant code from the UNSPSC excell sheet
Description of Requirements | Description of item required
PMU/End-User | Name of procuring unit/name of end user
Procurement Method | Competitive Bidding Method/Restricted Bidding Method/Direct Procurement Method/Request For Quotations method/Single-source selection method/Selection of Individual consultant method/Selection Amongst Community Service Organizations/Quality Based Selection/Quality and ost Based Selection/Least ost Selection/Expression of Intrest/Request for Proposal/Pre Qualification
EOI Publication Date | If required put dates or if not put "Not Applicable"
EOI Closing Date | If required put dates or if not put "Not Applicable"
Bid Notice Publication Date | Tentative date of tender notice publication date
Bid Closing Date | Tentative date of tender notice closing date
Publication of Award Notice | Tentative date of award notice publication date
Contract Signing | Tentative date of Signing of contract
Cycle(work days) Bid notice - Award notice | Total days required from tender publication to award publication
Lead Time (delivered time) Contract signing to expect. Delivery | Total days required from Contract signing to expected Delivery
SPOC (Y/N) | Mention Yes or No
Source of Funds | Mention source of fund to be used with code. Like Regular Agency Fund /Foreign Assisted Projects Fund /Special Account - Locally Funded/Domestic Grants Fund /Special Account - Foreign Assisted/Foreign Grants Fund /Internally Generated Funds/Business Related Funds/Trust Receipts/Others
Unit of Measurement (UoM) | Unit of measurement of the required quantity
Quantity | Quantity required
Unit Price | expected Per unit price of the required unit
Total(MOOE+CO) | For Estimated Budget (USD), kindly fill out either MOOE or CO columns only.
MOOE | Maintenance and Other Operating Expenses
CO | Capital Outlay (OR often referred to as CapEx or capital expenditures)
Comments | Brief description of program or project